## req_text
Sl No | Rdescription | Owner | Assinged on | Implemented On | Implemented By | Status | Remarks
1 | Capture Commodity details - Add in Gate-In Form (Change Stock Type to Commodity Type) (Garments, Auto Parts, Leather Garments, Shoe Uppers, Finish Leather, Console, Electrical & Electronics) - Jose (Venkat to send commodity details list) | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
2 | Return process to be detiailed | BVM Team | 2022-09-24 |  |  | Hold | Need inputs from Sridhar Sir
3 | Rename Loading Bay to Goods Receipt | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
4 | Add E,D,S prefix to customer code | BVM Team | 2022-09-24 |  |  | Hold | Need inputs from Sony/Venkat. Decided to provide manual input
5 | Add Not Available to OTL check in loading bay form | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
6 | Capture system timing for Unloading start & End Time | BVM Team | 2022-09-24 |  |  | Hold | Recommend to implement this feature after go-live.
7 | Arrival Date & Time in Gate-In screen renamed as Dock-In Date & Time | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
8 | Remove Dock-In Date & time form loading bay form | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
9 | Check customer contract validity on customer selection in Gate-In form | BVM Team | 2022-09-24 |  |  | YTS
10 | Notifications/alert for Customer Contract Validity, Warehouse Insurance Validity, Vendor contract Validity, E-way bill Validity | BVM Team | 2022-09-24 |  |  | YTS
11 | In Gate-In Form, if customer contract validity is expired, further steps should be allowed only for super user | BVM Team | 2022-09-24 |  |  | YTS
12 | In Gate-In form, change Invoice (actual) to Invoice weight-Gross(KG) | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
13 | Create Gate-In from Pre-Gate-In page | BVM Team | 2022-09-24 |  |  | Hold | Since it has one to many releationship, technically its not advisable to create WH job from Pre-gatein form
14 | Module List access and permissions | BVM Team | 2022-09-24 |  |  | YTS
15 | Change E-way bill validity date field to date & time | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
16 | Check E-way bill validity (alert has to 4hr before validity) | BVM Team | 2022-09-24 |  |  | YTS
17 | In Pre-Gate-In, add branch dropdown (for GRN purpose) | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
18 | In Pre-Check-In, add Shipment-Alert attachment (Shipment Information) | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
19 | In Pre-Check-In, Attachment for customer approval (in case of mismatch) | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
20 | In Billing, rate for all charges should be editable with concessional rate or Nil Billing with approval email from Customer/Joseph sire (Super user).Also, include comment box to document the change | BVM Team | 2022-09-24 |  |  | YTS
21 | In Customer master creation, super user to approve deviation in mandatory document (KYC, Contract, SOW, Operations SOP, Billing SOP,Rate Sheet) requirement with comments. Each document attachment field should have deviation (Yes/No), Frequency (Time being/Permanent)(Time being alert should be notified in alerts, Comments | BVM Team | 2022-09-24 |  |  | YTS
22 | In Damage Check/Before, change Damage Type to Multi select | BVM Team | 2022-09-24 |  |  | YTS
23 | In Damage Check/Before, generate GRN branch wise continuous number (Chennai-MAA, Bengaluru-BLR-XXXXXX) | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
24 | Continuous Job Number unitwise (Ex: MAA-U1-XXXX) | BVM Team | 2022-09-24 |  |  | Hold | Will be implemented during Go-Live
25 | Add GRN Number in Damage Check/After form | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
26 | Spell check Physical weight in Damage Check/After form | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
27 | In Damage Check/After Physical and Chargeable weight should be calculated for all box not for individual box | BVM Team | 2022-09-24 |  |  | Hold | At present Physical and Chargeable weight calculated for group of packages which is required to measure weight & Dimension deviation
28 | In Damage Check/After form add comment box to document deviations | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
29 | In Damage Check/After change damage check button name to inspection check report | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
30 | In Damage Check/After inspection report should be downloadable for any condition | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
31 | In Damage Check/After rename Damages as Overage/Shortage and mention the count in next text box and move to Damage Check/Before form | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed | Change in no of units deviation to be mentioned in comment box. For consistency, Overage/Shortages retained as "Quantity Change"
32 | In Damage Check/After move Ratification process to Damage Check/Before form | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
33 | In Damage Check/After move rename Quantity deviation as Quantity deviation (in open Box) and move to Damage Check/Before form | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
34 | In Damage Check/After add Fumigation Status (Yes/No). If fumigation is No then add a drop down with options (BVM,Customer) Venkat/Raghu to provide further process when fumigation Â come under BVM | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
35 | Add "Marks & numbers" (yes/no) in "Damage Check/Before". If No, hold the process and proceed upon customer approval | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
36 | Rename "Damage Check/Before" to "Check/Before offloading" and "Damage Check/After" to "Inspection" | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
37 | In Warehouse-In form, branch and unit should be tagged to user id | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed
38 | In Dispatch, add E-Waybill number, delivery challan | BVM Team | 2022-09-24 | 2023-01-01 | Jose | Completed | Like to know what content to be added in delivery Chellan
39 | In Dispatch, validate driver, truck, OTL with customer email | BVM Team | 2022-09-24 |  |  | Hold | Validation controlled by process
40 | In Loading Bay, move Dock-In time above Start time | BVM Team | 2022-09-24 |  |  | Hold | As per point 8, Dock-In time removed from loading bay form
41 | Share hardware configuration and cost for Tablet, QR Scanner, QR printer to BVM team | BVM Team | 2022-09-24 |  |  | YTS
42 | Schedule recurring meeting for every Saturday | BVM Team | 2022-09-24 |  |  | YTS
43 | in add/update insurance, include insured amount and premium | BVM Team | 2022-09-24 |  |  | YTS
44 | In customer data, add email field for operations lead | Sony | 2022-12-22 |  |  | YTS
45 | Remove Checked-In Status in Warehouse-In form | Jose | 2023-01-07 |  |  | YTS
46 | To be aligned as per the Process and not and alphabetic order | Jose | 2023-01-09 |  |  | YTS
47 | Commodity list to be provided for Masters | Venkat | 2023-01-09 |  |  | YTS
48 | Pre-Gatein (OTL, Lock & Key, NIL) | Jose | 2023-01-09 |  |  | YTS
49 | To work on Shipper invoice currency | Sridar Sir | 2023-01-09 |  |  | Cancelled | Currency value should match invoice. So existing process holds good.
50 | In Damage Check/Before Offloading change Quantity Deviation to Packages Deviation | Sridar Sir | 2023-01-09 |  |  | YTS
51 | In Damage Check/Before Offloading when Damages is not 'Nill Damage' or Quantity Devition or Ratification Process or Marks & Numbers is 'No' then Status should be 'Hold' | Sridar Sir | 2023-01-09 |  |  | YTS
52 | Include camera option to upload the pics. | Sridar Sir | 2023-01-09 |  |  | YTS
53 | Fumigation Status - Inspection screen | Sridar Sir | 2023-01-09 |  |  | YTS
54 | Check Fumigation | Sridar Sir | 2023-01-09 |  |  | YTS
55 | In the inspection tab capture the weight and no of pacakages deviation | Sridar Sir | 2023-01-09 |  |  | YTS
56 | In Warehouse in tab check no of pieces is considered forstorage. | Jose | 2023-01-09 | 2023-01-11 | Jose | Completed
57 | View option to be creasted for sridhar sir | Sridar Sir | 2023-01-09 |  |  | YTS
58 | DSR | Venkat | 2023-01-09 |  |  | YTS
59 | In storage report tab check the date formating for the check-out time | Sridar Sir | 2023-01-09 |  |  | YTS
60 | Packing Type : Wooden Case, Carton Box, Ply wood. If wooden case : Fumigation to appear. Fumigation : Yes & No. Yes to be completed. No : Customer or BVM (colour code). BVM : Date to be filled and accordingly. | Prakash | 2023-01-11 |  |  | YTS
61 | Dimension : Multiple line items to be clubbed | Prakash | 2023-01-11 |  |  | YTS
62 | Empty truck photo to be in warehouse in tab | Prakash | 2023-01-11 |  |  | YTS
63 | Multiple MAWB & HAWB to be added | Prakash | 2023-01-11 |  |  | YTS
64 | In warehousemaster rate form, bring customer short name in drop down | Sony | 2023-01-12 |  |  | YTS
65 | In Goods report form, headers are not alinged in with content. Check in similar forms as well. | Sony | 2023-01-12 |  |  | YTS
66 | Re-Order side Nave in WMS. Pre-Gate In, Warehouse Jobs, Goods Report, Dispatch, Invoice, Reports, WMS Misc. | Sony | 2023-01-12 | 2023-01-12 | Jose | Completed