## Requirements
Sl No | Backlogs | Module | Phase | Owner | Assigned on | Bug/Improvement? | Implemented On | Implemented By | Status | Remarks
1 | Capture Commodity details - Add in Gate-In Form (Change Stock Type to Commodity Type) (Garments, Auto Parts, Leather Garments, Shoe Uppers, Finish Leather, Console, Electrical & Electronics) - Jose (Venkat to send commodity details list) | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
2 | Return process to be detailed | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | Need inputs from Sridhar Sir
3 | Rename Loading Bay to Goods Receipt | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
4 | Add E,D,S prefix to customer code | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | Need inputs from Sony/Venkat. Decided to provide manual input
5 | Add Not Available to OTL check in loading bay form | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
6 | Capture system timing for Unloading start & End Time | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | Recommend to implement this feature after go-live.
7 | Arrival Date & Time in Gate-In screen renamed as Dock-In Date & Time | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
8 | Remove Dock-In Date & time form loading bay form | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
9 | Check customer contract validity on customer selection in Gate-In form | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
10 | Notifications/alert for Customer Contract Validity, Warehouse Insurance Validity, Vendor contract Validity, E-way bill Validity | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
11 | In Gate-In Form, if customer contract validity is expired, further steps should be allowed only for super user | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
12 | In Gate-In form, change Invoice (actual) to Invoice weight-Gross(KG) | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
13 | Create Gate-In from Pre-Gate-In page | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | Since it has one to many relationship, technically its not advisable to create WH job from Pre-gatein form
14 | Module List access and permissions | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
15 | Change E-way bill validity date field to date & time | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
16 | Check E-way bill validity (alert has to 4hr before validity) | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
17 | In Pre-Gate-In, add branch dropdown (for GRN purpose) | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
18 | In Pre-Check-In, add Shipment-Alert attachment (Shipment Information) | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
19 | In Pre-Check-In, Attachment for customer approval (in case of mismatch) | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
20 | In Billing, rate for all charges should be editable with concessional rate or Nil Billing with approval email from Customer/Joseph sire (Super user).Also, include comment box to document the change | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
21 | In Customer master creation, super user to approve deviation in mandatory document (KYC, Contract, SOW, Operations SOP, Billing SOP, Rate Sheet) requirement with comments. Each document attachment field should have deviation (Yes/No), Frequency (Time being/Permanent)(Time being alert should be notified in alerts, Comments | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
22 | In Damage Check/Before, change Damage Type to Multi select | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
23 | In Damage Check/Before, generate GRN branch wise continuous number (Chennai-MAA, Bengaluru-BLR-XXXXXX) | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
24 | Continuous Job Number unit wise (Ex: MAA-U1-XXXX) | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | Will be implemented during Go-Live
25 | Add GRN Number in Damage Check/After form | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
26 | Spell check Physical weight in Damage Check/After form | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
27 | In Damage Check/After Physical and Chargeable weight should be calculated for all box not for individual box | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | At present Physical and Chargeable weight calculated for group of packages which is required to measure weight & Dimension deviation
28 | In Damage Check/After form add comment box to document deviations | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
29 | In Damage Check/After change damage check button name to inspection check report | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
30 | In Damage Check/After inspection report should be downloadable for any condition | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
31 | In Damage Check/After rename Damages as Overage/Shortage and mention the count in next text box and move to Damage Check/Before form | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed | Change in no of units deviation to be mentioned in comment box. For consistency, Overage/Shortages retained as "Quantity Change"
32 | In Damage Check/After move Ratification process to Damage Check/Before form | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
33 | In Damage Check/After move rename Quantity deviation as Quantity deviation (in open Box) and move to Damage Check/Before form | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
34 | In Damage Check/After add Fumigation Status (Yes/No). If fumigation is No then add a drop down with options (BVM, Customer) Venkat/Raghu to provide further process when fumigation Â come under BVM | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
35 | Add "Marks & numbers" (yes/no) in "Damage Check/Before". If No, hold the process and proceed upon customer approval | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
36 | Rename "Damage Check/Before" to "Check/Before offloading" and "Damage Check/After" to "Inspection" | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
37 | In Warehouse-In form, branch and unit should be tagged to user id | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed
38 | In Dispatch, add E-Waybill number, delivery challan | WMS | 1 | BVM Team | 2022-09-24 | Improvement | 2023-01-01 | Jose | Completed | Like to know what content to be added in delivery Challan
39 | In Dispatch, validate driver, truck, OTL with customer email | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | Validation controlled by process
40 | In Loading Bay, move Dock-In time above Start time | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | Hold | As per point 8, Dock-In time removed from loading bay form
41 | Share hardware configuration and cost for Tablet, QR Scanner, QR printer to BVM team | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
42 | Schedule recurring meeting for every Saturday | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
43 | In add/update insurance, include insured amount and premium | WMS | 1 | BVM Team | 2022-09-24 | Improvement |  |  | YTS
44 | In customer data, add email field for operations lead | WMS | 1 | Sony | 2022-12-22 | Improvement |  |  | YTS
45 | Remove Checked-In Status in Warehouse-In form | WMS | 1 | Jose | 2023-01-07 | Improvement |  |  | YTS
46 | To be aligned as per the Process and not and alphabetic order | WMS | 1 | Jose | 2023-01-09 | Improvement |  |  | YTS
47 | Commodity list to be provided for Masters | WMS | 1 | Venkat | 2023-01-09 | Improvement |  |  | YTS
48 | Pre-Gatein (OTL, Lock & Key, NIL) | WMS | 1 | Jose | 2023-01-09 | Improvement |  |  | YTS
49 | To work on Shipper invoice currency | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | Cancelled | Currency value should match invoice. So existing process holds good.
50 | In Damage Check/Before Offloading change Quantity Deviation to Packages Deviation | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | Completed | Retaining "Quantity Deviation" instead of "Package Deviation"
51 | In Damage Check/Before Offloading when Damages is not 'Nil Damage' or Quantity Deviation or Ratification Process or Marks & Numbers is 'No' then Status should be 'Hold' | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | Completed | Retaining "Work In Progress" instead of hold.
52 | Include camera option to upload the pics. | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | YTS
53 | Fumigation Status - Inspection screen | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | Completed
54 | Check Fumigation | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | Completed
55 | In the inspection tab capture the weight and no of packages deviation | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | YTS
56 | In Warehouse in tab check no of pieces is considered for storage. | WMS | 1 | Jose | 2023-01-09 | Improvement | 2023-01-11 | Jose | Completed
57 | View option to be created for Sridhar sir | WMS | 1 | Sridhar Sir | 2023-01-09 | Improvement |  |  | YTS
58 | DSR | WMS | 1 | Venkat | 2023-01-09 | Improvement | 2023-05-07 | Jose | Completed
59 | In storage report tab check the date formatting for the check-out time | WMS | 1 | Sridhar Sir | 2023-01-09 | Bug | 2023-01-14 | Jose | Completed
60 | Packing Type : Wooden Case, Carton Box, Ply wood. If wooden case : Fumigation to appear. Fumigation : Yes & No. Yes to be completed. No : Customer or BVM (color code). BVM : Date to be filled and accordingly. If fumigation done by BVM then, the cost should be included in billing. | WMS | 1 | Prakash | 2023-01-11 | Improvement | 2023-01-14 | Jose | Completed | Billing for fumigation alone pending
61 | Dimension : Multiple line items to be clubbed | WMS | 1 | Prakash | 2023-01-11 | Improvement | 2023-05-07 | Jose | Completed
62 | Empty truck photo to be in warehouse in tab | WMS | 1 | Prakash | 2023-01-11 | Improvement |  |  | Cancelled | Already available in "Damage Check Before/Offloading" form
63 | Multiple MAWB & HAWB to be added | WMS | 1 | Prakash | 2023-01-11 | Improvement |  |  | YTS
64 | In warehouse master rate form, bring customer short name in drop down | WMS | 1 | Sony | 2023-01-12 | Improvement | 2023-05-07 | Jose | Completed
65 | In Goods report form, headers are not aligned in with content. Check in similar forms as well. | WMS | 1 | Sony | 2023-01-12 | Bug |  |  | WIP
66 | Re-Order side Nave in WMS. Pre-Gate In, Warehouse Jobs, Goods Report, Dispatch, Invoice, Reports, WMS Misc. | WMS | 1 | Sony | 2023-01-12 | Improvement | 2023-01-12 | Jose | Completed
67 | In Stock Value report, round off total to 2 decimal places. | WMS | 1 | Jose | 2023-01-12 | Improvement | 2023-01-12 | Jose | Completed
68 | In Gate-In Form, don’t show pre-gatein ID's for checked out jobs | WMS | 1 | Jose | 2023-01-13 | Improvement |  |  | Cancelled | Since pre-gatein number linked to multiple WH jobs, its not possible to remove from list.
69 | WMS dashboard: Pending for invoice and bring reports to WH dashboard | WMS | 1 | Sony | 2023-01-14 | Improvement |  |  | YTS
70 | In invoice, partial billing to be calculated. | WMS | 1 | Sony | 2023-01-14 | Improvement |  |  | YTS
71 | In WMS dashboard, show goods older than 7 days | WMS | 1 | Sony | 2023-01-14 | Improvement |  |  | YTS
72 | Add total invoice weight in inspection sheet. Entering weight for each box is not feasible. | WMS | 1 | Venkat | 2023-01-18 | Improvement |  |  | Hold | To be discussed with Sridhar Sir
73 | Check INR Calculation | WMS | 1 | Venkat | 2023-01-18 | Bug | 2023-01-19 | Jose | Completed
74 | Add PO number | WMS | 1 | Venkat | 2023-01-18 | Improvement | 2023-01-25 | Jose | Completed
75 | Check chargeable weight and CBM calculation | WMS | 1 | Venkat | 2023-01-18 | Bug | 2023-01-18 | Jose | Completed
76 | Prepare sock report as per DSR shared by Venkat | WMS | 1 | Venkat | 2023-01-18 | Improvement | 2023-05-07 | Jose | Completed
77 | In inspection form, Add goods count & weight comparison between invoice and check-In | WMS | 1 | Jose | 2023-01-25 | Improvement | 2023-01-25 | Jose | Completed
78 | In Inspection form, check-In weight and count throwing round off error | WMS | 1 | Prakash | 2023-01-27 | Bug | 2023-01-27 | Jose | Completed
79 | In inspection form, remove validation for excess weight | WMS | 1 | Prakash | 2023-01-30 | Improvement | 2023-01-31 | Jose | Completed
80 | Once Dispatch status is completed, update Dispatch status t "Yes" in gatein table database | WMS | 1 | Prakash | 2023-01-30 | Improvement | 2023-01-31 | Jose | Completed
81 | Audit Module for TMS WMS PMS - Audit Manual, checklist, score card and reports | WMS,TMS,PMS | 2 | Sridhar Sir | 2023-02-03 | Improvement |  |  | YTS | Sridhar sir to provide detailed requirement.
82 | Sales Management System (SMS) | WMS | 1 | Sridhar | 2023-02-03 | Improvement | 2023-03-26 | Jose | Completed | Sridhar sir to provide detailed requirement.
83 | Insurance Module to be changed | WMS | 1 | Sridhar | 2023-02-03 | Improvement | 2023-02-11 | Jose | Completed | Sony to provide more details.
84 | Budget Master to be created. Branch, Unit, Expense type, amount, month | WMS | 1 | Sridhar Sir | 2023-02-03 | Improvement |  |  | YTS | Sony to provide more details.
85 | In expense add form, service start and end date to be same | WMS | 1 | Sridhar Sir | 2023-02-03 | Improvement |  |  | YTS | Sony to provide more details.
86 | Income Master line item to be defined | WMS | 1 | Sridhar Sir | 2023-02-03 | Improvement |  |  | YTS | Sony to provide more details.
87 | Check remarks field for Inward, storage and dispatch | WMS | 1 | Sridhar Sir | 2023-02-03 | Improvement |  |  | YTS
88 | In Dispatch form, increase text field size | WMS | 1 | Prakash | 2023-02-16 | Improvement | 2023-02-16 | Jose | Completed
89 | Create route master | TMS | 1 | Sony | 2023-02-18 | Improvement |  |  | YTS
90 | In Trip details, move 'Delivery Image' and 'Proof Of Delivery' to Trip closure. | TMS | 1 | Sony | 2023-02-18 | Improvement |  |  | YTS
91 | In Vehicle master, vehicle details, engineer number should be alpha numeric | TMS | 1 | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
92 | In Vehicle master, vehicle details battery number should be alpha numeric | TMS | 1 | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
93 | In Vehicle master, insurance details insurance copy should be attachable | TMS | 1 | Karthik | 2023-02-18 | Improvement |  |  | YTS
94 | In Vehicle master, RTO details FC copy should be attachable | TMS | 1 | Karthik | 2023-02-18 | Improvement |  |  | YTS
95 | In Vehicle master, RTO details Road Tax copy should be attachable | TMS | 1 | Karthik | 2023-02-18 | Improvement |  |  | YTS
96 | In Vehicle master, Permit and pollution control details permit copy should be attachable | TMS | 1 | Karthik | 2023-02-18 | Improvement |  |  | YTS
97 | In Vehicle master, Permit and pollution control details pollution certificate copy should be attachable | TMS | 1 | Karthik | 2023-02-18 | Improvement |  |  | YTS
98 | In vendor add form, GSTIN number set size to 15 | TMS | 1 | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
99 | In Expense add form, split total bills into multiple line items. | TMS | 1 | Blessy | 2023-02-18 | Improvement |  |  | YTS
100 | In Vehicle master, change ICV to IDV | TMS | 1 | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
101 | In Consignment note add, add customer code | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
102 | In Enquiry note add, assigned to should be from login user | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
103 | In Consignment note add, add touch point between from and to | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
104 | In Consignment add, consigner, consignee, Consigner Invoice, Consigner Value, Value in INR, No of Pieces, weight to be added as separate line item | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
105 | In Consignment add, move ebill no, date of Issue, Date of validity to trip details form | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
106 | In Consignment add, remove 'Container' for 'Container Description' label. | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
107 | In Consignment add, remove Dimension | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
108 | In Consignment add, add 'Movement type' with FTL, LTL as drop down | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
109 | In Consignment add, change 'Movement' to 'Consignment Type' | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
110 | In Consignment add, change 'Movement' to 'Consignment Type' | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
111 | In Consignment add, add 'Freight Amount' | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
112 | In Trip details add, include 'Billing Type' drop down. Vehicle Type Requested, Vehicle Type Placed | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
113 | In Trip details add, change 'Vehicle Type' label to 'Vehicle Type Placed'. | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
114 | In Trip details add, update driver name as drop down and pull license number, contact number from database | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
115 | In Trip details add, From Location, To Location, Starting Km, Ending KM, Starting Date, Ending Date as separate Row Items | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
116 | In Trip closure, change 'cost' in all labels to 'Charges' | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
117 | In Trip closure, add 'Handling Charges and Halting Charges | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
118 | In Trip closure, add customer ref no | TMS | 1 | Sony | 2023-02-21 | Improvement |  |  | YTS
119 | In Damage check after, unable to add new line item | WMS | 1 | Prakash | 2023-02-22 | Improvement | 2023-02-23 | Jose | Completed
120 | In dispatch list, MAWB & HAWB numbers were same. | WMS | 1 | Prakash | 2023-02-24 | Bug | 2023-02-24 | Jose | Completed
121 | In warehouse goods model file, shipper invoice value is incorrect. | WMS | 1 | Prakash | 2023-03-18 | Bug | 2023-03-18 | Jose | Completed
122 | Create separate customer database for warehouse transport, packing | WMS,TMS,PMS | 1 | Sony | 2023-03-28 | Improvement |  |  | YTS
123 | While sharing parent screen is not appearing another screen | Sales | 1 | Sony | 2023-03-28 | New Requirement |  |  | Cancelled | Not an issue with application. Issues resolved when entire screen is shared than sharing only the application.
124 | In Customer Master add BVM Business (BVM Trans Solution, BVM Pack Solutions, BVM Storage Solutions), attachment for Contract, Contract Validity date From and To TO | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-04-18 | Jose | Completed
125 | In revenue report, BVM company wise report to be generated. | Sales-PBI | 1 | Sony | 2023-03-28 | New Requirement | 2023-07-15 | Alain | Completed
126 | In Sale form, Requirement : not required | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
127 | Manpower to be changed as Other Requirement with Open text box | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
128 | Day call to be removed from Transport requirement drop down | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
129 | Wooden Box Spelling | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
130 | To check for BVM Admin to add Product master in each vertical | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
131 | Type of supply to be enable only for packing requirement and mandatory | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed | KT provided to Sony
132 | Location to be renamed as handling office | Sales | 1 | Sony | 2023-03-28 | New Requirement |  |  | Cancelled | change not required
133 | Is customer name to have location as suffix also or location to be in separate field | Sales | 1 | Sony | 2023-03-28 | New Requirement |  |  | Cancelled | change not required
134 | Type of Call : TO have E-mail as an option | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
135 | Nature of Call : To have Existing as an option | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
136 | Purpose of Call : Customer complaint, After Sales | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
137 | Decision maker : Not applicable refers to whom (remove Not applicable) | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
138 | Joint Call : Yes/No to be created | Sales | 1 | Sony | 2023-03-28 | New Requirement |  |  | Cancelled | change not required
139 | Volume/Business potential to be separated | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
140 | Prospective custom : Not applicable ro be removed | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
141 | Prospective custom : If No drop down to be added | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed | Rate not competitive, Business model not viable, Customer well aligned with current vendor, Not immediate,
142 | Business won: If No drop down to be added | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed | Not competitive, sales closing not effective, late response
143 | Date of quote sent till business win date system to trigger a dash board with data of quote sent vs business win (Calculate no of days between quote sent and business start) | Sales | 1 | Sony | 2023-03-28 | New Requirement |  |  | Completed
144 | Status: Business started, Customer response pending | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
145 | Sales Call Owner name field required | Sales | 1 | Sony | 2023-03-28 | New Requirement |  |  | Cancelled | change not required
146 | Customers Revenue to be aligned with the sales person | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
147 | Weekly sales report template | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
148 | date range | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
149 | name of the sales person | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
150 | list of customers/ no of calls | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
151 | current status | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
152 | date of business start | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
153 | billing done as on date for the month | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
154 | AR as on date | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
155 | Customer code field to be created | Sales | 1 | Sony | 2023-03-28 | New Requirement |  |  | Cancelled | change not required
156 | Manpower Requirement to be removed and added in Facility managed | Sales | 1 | Sony | 2023-03-28 | New Requirement | 2023-03-30 | Jose | Completed
157 | add Status, quote sent date, business start date in list page and difference | Sales | 1 | Sony | 2023-09-30 | New Requirement | 2023-03-30 | Jose | Completed
158 | Add auto generated filed for sales order number | Sales | 1 | Sony | 2023-09-30 | New Requirement | 2023-04-01 | Jose | Completed
159 | In customer add form, check mandatory fields for customer contact, email etc. | WMS | 1 | Sony | 2023-04-01 | Bug | 2023-04-02 | Jose | Completed
160 | In Invoice add form, change e-invoice number as non-mandatory | WMS | 1 | Sony | 2023-04-01 | Bug | 2023-04-02 | Jose | Completed
161 | In Invoice add & list page, change voucher number to BVM invoice number | WMS | 1 | Sony | 2023-04-01 | Bug | 2023-04-02 | Jose | Completed
162 | In sales form, add attachment field for "Visiting card" and "Review Presentations" | Sales | 1 | Sony | 2023-04-03 | New Requirement | 2023-04-05 | Jose | Completed
163 | In Sales form, add comments section as separate line item | Sales | 1 | Sony | 2023-04-03 | New Requirement | 2023-04-05 | Jose | Completed
164 | In Invoice form, loading and unloading charges calculation incorrect | Invoice | 1 | Sony | 2023-04-05 | Bug | 2023-04-12 | Jose | Completed
165 | In Invoice list, stock not moving to open pool once invoice number is deleted | Invoice | 1 | Sony | 2023-04-05 | Bug | 2023-04-12 | Jose | Completed
166 | In Sales list report, change "Created By" to "Owned By" | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-04-18 | Jose | Completed
167 | Need sales report separately. Detailed report: Sales list fields add on field Summary Report: Sales person Name, number of new customer, ,Existing, number of calls, location, date range. | Sales-PBI | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-30 | Jose | Completed | 23-Jun-23 (Jose) Reports developed in PowerBi. Under BVM review (Sony)
168 | Change "Location" to "Handling Branch" | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-04-18 | Jose | Completed
169 | Change "Add" to Insert | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-04-18 | Jose | Completed
170 | In Add on form, add "Date of Call" with current & previous date lock. | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-04-18 | Jose | Completed
171 | In Add on form, add "Customer Name" | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement |  |  | Cancelled | Tagged to main sales form. Hence ignored
172 | In main sales form and add on form, super user should have access to change | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement |  |  | Cancelled
173 | In Add on form, insert "Complaints" field from main form | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-04-18 | Jose | Completed
174 | In Add on form, insert "Compliment" field from main form | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-04-18 | Jose | Completed
175 | In man form, Existing customer, new customer, customer type as mandatory field | Sales | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-04-18 | Jose | Completed
176 | Capture Unbilled AR to be connected with billing cycle of every customer. | AR | 1 | Sridhar Sir | 2023-04-15 | Improvement |  |  | YTS
177 | Develop add page fo Accounts Recieveable (AR) input | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
178 | Develop list page fo Accounts Recieveable (AR) input | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
179 | Develop views for AR insert | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
180 | Develop views for AR Update | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
181 | Develop views for AR list | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
182 | Develop views for AR delete | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
183 | Develop logic to calculate Due from operation date, Submission date, Invoice date | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
184 | Develop logic to calculate received from operation date, Submission date, Invoice date | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
185 | Develop logic to calculate total payment and balance paymnet | AR | 1 | Sridhar Sir | 2023-04-15 | New Requirement | 2023-06-20 | Jose | Completed
186 | AR ageing from Invoice generation date(0-30,31-45,46-60,61-75,76-90,91-120,121-150,151-180,181-365,>365) | AR-PBI | 1 | Sridhar Sir | 2023-04-15 | Improvement | 2023-06-20 | Jose | Completed
187 | Include billing cycle. Connect with Business Model and business solution | Customer | 1 | Sridhar Sir | 2023-04-15 | Improvement | 2023-04-18 | Jose | Completed
188 | Generation of airline stickers with control on cross labelling | WMS | 2 | Sridhar Sir | 2023-04-15 | Improvement |  |  | YTS
189 | Escalation module in mobile app fro Joseph | WMS,TMS,PMS | 2 | Sridhar Sir | 2023-04-15 | Improvement |  |  | YTS
190 | In dispatch form when Fumigation status is "Yes" and Fumigation date is not entered, don’t allow to checkout the goods. | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-26 | Jose | Completed
191 | In Stock Value report, check Destination, HAWB, CB, UOM, Eway Bill | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-15 | Jose | Completed
192 | In Stock Value report, add "Out" details | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-15 | Jose | Completed
193 | In Stock Value report, "Case No" = "PO" | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-04 | Jose | Completed
194 | In Gate-In form add "Destination" | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-04 | Jose | Completed
195 | In Gate-In form add "HAWB" | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-04 | Jose | Completed
196 | In Gate-In form add "S-bill #" & "S-bill Date" and ensure it is entered during checkout. | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-26 | Jose | Completed
197 | In Dispatch form, add ship date & time | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-04 | Jose | Completed
198 | In Dispatch form, add Truck out date & time | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-04 | Jose | Completed
199 | In Gate-In form add "MAWB" & "HAWB" number | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-04 | Jose | Cancelled | As per discussion with Prakash on 04-May-23, we decided to add only HAWB in gate-in form
200 | In dispatch form, remove "HAWB" number | WMS | 1 | Prakash | 2023-03-30 | Improvement | 2023-05-04 | Jose | Completed
201 | In Invoice add form, crane and forklift charges should be Zero when invoice is not added | WMS | 1 | Sony | 2023-05-08 | Bug | 2023-05-08 | Jose | Completed
202 | In AR add form, add input field for total payment and balance payment | WMS | 1 | Sony | 2023-05-13 | Improvement | 2023-05-13 | Jose | Completed
203 | In Dispatch add form, remove Shipping Date. | WMS | 1 | Prakash | 2023-05-13 | Improvement | 2023-05-13 | Jose | Completed
204 | In Dispatch list form, Sticker Fixed Value not populating | WMS | 1 | Prakash | 2023-05-13 | Bug | 2023-05-13 | Jose | Completed
205 | In Gate-In list form, dispatch status is incorrect | WMS | 1 | Venkat | 2023-05-13 | Bug | 2023-05-15 | Jose | Cancelled | No issues observed. MAA_WH_Job_270649,Dispatch_127774
206 | In Invoice list form, loading and unloading charges to be calculated separately for each job number. | WMS | 1 | Sony | 2023-05-13 | Improvement | 2023-05-18 | Jose | Completed
207 | In Dispatch form, waybill not populated properly | WMS | 1 | Venkat | 2023-05-15 | Bug | 2023-05-15 | Jose | Completed
208 | In Stock report, show gross weight and total package count (physical) | WMS | 1 | Venkat | 2023-05-15 | Improvement | 2023-05-15 | Jose | Completed
209 | In inspection form, check volume weight formula. | WMS | 1 | Venkat | 2023-05-15 | Bug | 2023-05-15 | Jose | Completed | Venkat confirmed to link chargeable weight
210 | In Inspection report, FUMIGATION SHOULD BE Y/N | WMS | 1 | Venkat | 2023-05-15 | Bug | 2023-05-15 | Jose | Completed
211 | In Stock report, DESTINATION COLUMN - NOT SHOWING DEST | WMS | 1 | Venkat | 2023-05-15 | Bug | 2023-05-15 | Jose | Completed | Venkat confirmed to link destination in Gate-In form for stock report
212 | Random numbers duplicate in WH_Job, GRN, Stock numbers | WMS | 1 | Prakash | 2023-05-17 | Bug | 2023-05-18 | Jose | Completed
213 | After saving Gate-In, Goods-Receipt, Damage Check Before/after, Inspection, Warehouse-In, Storage forms stay back in same page. | WMS | 1 | Prakash | 2023-05-17 | Bug | 2023-05-18 | Jose | Completed
214 | Feature to upload RC, Road Tax, Insurance, Permit, Pollution | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
215 | GPS Integration | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
216 | Fastag Integration | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
217 | Customizable DSR (Key Challenge) | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
218 | Update POD submission date (key challenge) | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
219 | In enquiry form add, CHB, Transcon, Order Management in Customer department | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
220 | In enquiry form, Pre-Select customer department, contact, email based on customer selection | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
221 | In enquiry form, Pre-select BVM Customer service person (Assigned To) based on login | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
222 | In customer add form, tag BVM Customer service person, customer department and its contact (name, email, mobile number) | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
223 | In enquiry form, add pick up date and time | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
224 | In Consignment add form, create master consigner and consignee list | TMS | 2 | Prem | 2023-05-20 | Improvement |  |  | YTS
225 | In Consignment add form, change "Ebill no" to "Eway Bill No" | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
226 | In Consignment add form, remove "Dimensions" | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
227 | In Consignment add form, add "Customer Reference Number" as non mandatory field | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
228 | In Consignment add form, add "Customer Reference Number Mandatory?" as yes/no field. If No, pick shipper invoice number for invoice. | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
229 | In Consignment add form, make changes to add multiple rows for all fields | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
230 | In Consignment add form, add "Business Type" | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
231 | In trip details add form, remove "Business Type" | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
232 | In trip details add form, "Starting Date" should be Date-Time type | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
233 | In trip details add form, "Ending Date" should be Date-Time type | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
234 | In trip details add form, add "Reporting-Time", "Dock-In Time", Dock-Out Time" for from and to locattion | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
235 | Add "Order Allocation" in TMS for vehicle assignment and base trip creations | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
236 | Add "Vehicle Availability" in TMS (vehicle num, type, location, date-time) | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
237 | In consignment note, option to add & delete shipper invoices | TMS | 1 | Prem | 2023-05-20 | Improvement |  |  | YTS
238 | In Dispatch master stock list, add number of qty. | WMS | 1 | Venkat | 2023-05-20 | Improvement | 2023-05-26 | Jose | Completed
239 | In Stock Report, calculate total qty and gross weight based on supplier invoice | WMS | 1 | Venkat | 2023-05-20 | Improvement |  |  | YTS
240 | In Stock Report, check Date-Time format in downloaded excel | WMS | 1 | Venkat | 2023-05-20 | Improvement |  |  | YTS
241 | In WH Job list include HAWB number | WMS | 1 | Venkat | 2023-05-20 | Improvement | 2023-05-26 | Jose | Cancelled | Not possible
242 | Create separate form for crane and forklift calculation | WMS | 1 | Venkat | 2023-05-20 | Improvement |  |  | Cancelled | Covered under loading bay section
243 | In Sales Reort, add fields for Target calls and revenue | Sales | 1 | Sony | 2023-05-22 | New Requirement | 2023-05-23 | Jose | Completed
244 | In Sales add edit form, input validation not happening | Sales | 1 | Raghu | 2023-05-26 | New Requirement | 2023-05-26 | Jose | Completed
245 | In Trip details add form inlcude weighment cost. | TMS | 1 | Sony | 2023-06-28 | Improvement |  |  | YTS
246 | In Asset add form, add asset ID field | Assets | 1 | Sony | 2023-06-30 | Improvement | 2023-06-30 | Jose | Completed
247 | In asset add form,Unit should be listed based on location | Assets | 1 | Sony | 2023-06-30 | Improvement | 2023-06-30 | Jose | Completed
248 | In Asset QR code, add 'Product' to the List | Assets | 1 | Sony | 2023-06-30 | Improvement | 2023-06-30 | Jose | Completed
249 | In dispatch add and list form, include Shipper invoice details | WMS | 1 | Jose | 2023-07-03 | Improvement | 2023-07-03 | Jose | Completed
250 | In asset add form, Unit list incorect for selcted branches | Assets | 1 | Sony | 2023-07-03 | Bug | 2023-07-04 | Jose | Completed
251 | In Sales, make Business Not Won as mandatory field. | Sales | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-06 | Jose | Completed
252 | In Ar add & list form, include sales person name | AR | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-06 | Jose | Completed
253 | In Sales PowerBi reports, add slicer for sales executive wise | Sales-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-15 | Alain | Completed
254 | In AR, make provision to add payment followup comments (Date, Customer contact name, Designation, BVM login name and remarks) | AR | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-19 | Jose | Completed
255 | In Ar, include sales person Name (Amount Yet to Received chart) | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-04 | Jose | Completed
256 | In AR PowerBi report, add slicer for customer name (Amount Yet to Received chart) | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-15 | Alain | Completed
257 | In Stock report, show cost denominations in Lakhs & Crores | WMS-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-20 | Alain | Completed
258 | In Stock report, generate alert when total In-Bound stock value crosses 20Cr, alert Sony | Alerts | 1 | Sridhar Sir | 2023-07-04 | Improvement |  |  | YTS
259 | In AR, add slicer to aging time (16-30, 46-60...) | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-15 | Alain | Completed
260 | In AR, add ageing 91-120,121-150, 151-180,181>above | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-15 | Alain | Completed
261 | In AR, show Amount Received chart separately | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-15 | Alain | Completed
262 | In AR, show slicer for received Date in Amount Received chart | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-20 | Alain | Completed
263 | In Ar, include sales person Name ( Amount Received chart) | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-15 | Alain | Completed
264 | In AR PowerBi report, add slicer for customer name ( Amount Received chart) | AR-PBI | 1 | Sridhar Sir | 2023-07-04 | Improvement | 2023-07-15 | Alain | Completed
265 | In Invoice, check open invoice list | Invoice | 1 | Sony | 2023-07-10 | Bug | 2023-07-24 | Jose | Completed
266 | In Invoice list below invoice add, include 'Vehicle Type' and shipper name. | Invoice | 1 | Sony | 2023-07-10 | Bug | 2023-07-12 | Jose | Completed
267 | In Invoice list below invoice add, include export csv, excel option | Invoice | 1 | Sony | 2023-07-10 | Bug | 2023-07-12 | Jose | Completed
268 | In warehousejobs/inspection add page, save record only if the stock weight is within 5% deviation. | Invoice | 1 | Sony | 2023-07-10 | Improvement |  |  | YTS
269 | In Invoice, Loading and unloading cost to be calculated based on total qty and weight for each shipper invoice | Invoice | 1 | Sony | 2023-07-11 | Improvement | 2023-07-12 | Jose | Completed
270 | In invoice, Billing start date and end date to be auo populated from shippment in & out date time for case to case customer | Invoice | 1 | Sony | 2023-07-11 | Improvement | 2023-07-12 | Jose | Completed
271 | In invoice, Billing start date and end date to be entered manually for exclusive & Dedicated customer | Invoice | 1 | Sony | 2023-07-11 | Improvement | 2023-07-12 | Jose | Completed
272 | In Invoice report list, add vehicle type and re-check all paramaeters | Invoice | 1 | Sony | 2023-07-11 | Improvement | 2023-07-15 | Jose | Completed
273 | In Sales List page, add button to include comments list | Sales | 1 | Sony | 2023-07-14 | Improvement | 2023-07-15 | Jose | Completed
274 | Stock report not working | WMS | 1 | Prakash | 2023-07-24 | Bug | 2023-07-24 | Jose | Completed
275 | In WH rate master, included min area and max areas fields to calculate warehouse charges for dedicated and exclusive customers | WMS | 1 | Sony | 2023-07-18 | Improvement | 2023-07-24 | Jose | Completed
276 | In asset list, add brancha nd unit | Assets | 1 | Jose | 2023-07-24 | Improvement | 2023-07-26 | Jose | Completed
277 | In Customer add form, unable to add new recoord | Customer | 1 | Kanchana | 2023-07-26 | Bug | 2023-07-26 | Jose | Completed
278 | In home page, add open invoice list for Case_to_case, dedicated and exclusive customers | Invoice | 1 | Sony | 2023-07-25 | Bug | 2023-07-26 | Jose | Completed
279 | Dispatch add/edit not getting saved | WMS | 1 | Kanchana | 2023-07-27 | Bug | 2023-07-27 | Jose | Completed
280 | In Sales list, add "Joint Call", "Business Won" | Sales | 1 | Sony | 2023-07-31 | Improvement | 2023-07-31 | Jose | Completed
281 | In Sales add/edit, freeze date of call. Only yesterday and today date should be displayed | Sales | 1 | Sony | 2023-07-31 | Improvement |  |  | YTS
282 | In Stock report, add destination, invoive weight, qty, check in weight ,qty, truck number, truck type truck out time, e-way bill number | WMS | 1 | Prakash | 2023-07-31 | Improvement | 2023-07-31 | Jose | Completed
283 | In warehouse in, check bay number for chennai, unit 3 | WMS | 1 | Prakash | 2023-07-31 | Improvement | 2023-08-01 | Jose | Completed
284 | In stock report, Loading and unloading time only | WMS | 1 | Prakash | 2023-08-01 | Improvement |  |  | YTS
285 | In stock report,move MAWB number to last column | WMS | 1 | Prakash | 2023-08-01 | Improvement | 2023-08-01 | Jose | Completed
286 | In stock report,add e-wabill validity date next to ewaybill number | WMS | 1 | Prakash | 2023-08-01 | Improvement | 2023-08-01 | Jose | Completed
287 | Check currency type coversion | WMS | 1 | Prakash | 2023-08-01 | Improvement | 2023-08-01 | Jose | Completed
288 | Remove eway bill, destination, MAWB number from dispatch add | WMS | 1 | Prakash | 2023-08-01 | Improvement | 2023-08-01 | Jose | Completed | (01-Aug-2023) Jose MAWB number retained. Will be disucssed further with Prakash
289 | In Pre-Gate-in, increase field size for truck number, driver name, number, DL number | WMS | 1 | Prakash | 2023-08-01 | Improvement | 2023-08-01 | Jose | Completed
290 | In Gate-in, increase field size for invoice and PO number | WMS | 1 | Prakash | 2023-08-01 | Improvement | 2023-08-01 | Jose | Completed
291 | In Goods-Receipt, check forklift and crane time & charge calculations | WMS | 1 | Prakash | 2023-08-01 | Improvement |  |  | YTS
292 | In Customer call report, Customer name and comments (no of visits to this customer) to be displayed once customer type count is clicked for the selected sales executive | Sales-PBI | 1 | Sony | 2023-08-01 | Improvement |  |  | YTS
293 | Tag Invoice against sale order or Sales executive | Sales-PBI | 1 | Sony | 2023-08-01 | Improvement | 2023-08-01 | Jose | Completed

## Expense
BRANCH | UNIT | VENDOR | VENDOR BILL NO | VENDOR BILL DATE | Service Start Date | Service End Date | EXPENSE Type | UNIT OF MEASUREMENT | RATE | REMARKS | QUANTITY | AMOUNT | GST RATE % | GST AMOUNT | TOTAL AMOUNT | TDS RATE % | TDS AMOUNT | AMOUNT PAYABLE | DUE DATE | PAID DATE
FK | FK | FK | text | Date |  |  | Man power | FK | Float | textarea | int | float | float | float | float | float | float | float | date | date
[7 empty] | rent | Sqt |  |  |  |  | 18% |  |  |  | amount*tds rate | tot amount-tds amount | bill date +vendor payment (check vendor database)
[7 empty] | security | Nos
hrs

## Progress
Phase | (Multiple Items)
Count of Sl No | Column Labels
Row Labels | Bug | Improvement | New Requirement | Grand Total
Completed | 22 | 84 | 51 | 157
YTS | 1 | 88 |  | 89
Cancelled | 1 | 6 | 8 | 15
Hold |  | 9 |  | 9
WIP | 1 | 2 |  | 3
Grand Total | 25 | 189 | 59 | 273
Count of Sl No | Column Labels
Row Labels | AR | AR-PBI | Assets | Customer | Invoice | Sales | Sales | Sales-PBI | TMS | WMS | Grand Total
Jan | [9 empty] | 36 | 36
Feb | [8 empty] | 4 | 4 | 8
Mar | [6 empty] | 26 |  |  | 2 | 28
Apr |  |  |  | 1 | 2 |  | 11 |  |  | 3 | 17
May | [6 empty] | 2 |  |  | 30 | 32
Jun | 9 |  | 3 |  |  |  |  | 1 |  |  | 13
Jul | 2 | 7 | 1 |  | 6 | 1 | 1 | 2 |  | 1 | 21
Grand Total | 11 | 7 | 4 | 1 | 8 | 1 | 40 | 3 | 4 | 76 | 155

## Project_Progress
Module | SMS (Sales) | FMS (AR) | WMS (Warehouse) | PMS (Packing) | TMS (Transport) | CMS (Customer) | VMS (Vendor) | Admin | AMS (Assets) | EMS (Employee) | Reports (PBI) | Acceptance Criteria | Remarks
Priority | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
% Completion | 98% | 98% | 98% | 10% | 50% | 98% | 98% | 98% | 98% | 98% | 30%
Internal Rollout for testing | 2023-05-01 | 2023-06-15 | 2023-01-01 | 2023-09-01 | 2023-08-15 | 2023-01-01 | 2023-01-01 | 2023-01-01 | 2023-01-01 | 2023-01-01 | 2023-10-15
Bugs & Improvements | 2023-05-19 | 2023-06-24 | 2023-05-19 | 2023-09-15 | 2023-08-30 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2023-11-15
Additional Testing | 2023-05-25 | 2023-06-30 | 2023-05-25 | 2023-09-30 | 2023-09-15 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 2023-12-01
Final Deployment (Operational) | 2023-06-01 | 2023-07-01 | 2023-06-01 | 2023-10-15 | 2023-09-30 | 2023-05-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-12-01 | DSR & Stock report as per customer requirement | Implemented
Final Deployment (Finance) | 2023-06-30 | 2023-07-15 | 2023-07-15 | 2023-10-30 | 2023-10-15 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-12-20

## Sales
Facility Mgt | Manpower Mgt | Supply | Call-Type | Nature Of Call | Purpose of Call
Stationary | Handlers | Manufcturing | In-Person | New-First Time | Sales Call | Split name of the decision maker and Designation
Hous keeping | Supervisors | Trading | Tele-Call | Target-Till Quote | Followup Call | Disable date of call
|  | value added | MS-Teams | Pipeline-Till PO | Review Meeting | If No, Reason? (free Text)
|  |  |  | Existing | Escalation Meeting | Expected Profit %, Integer
[5 empty] | Rate Revision | Approver Name (Joseph Sony)
[5 empty] | Survey | Status - Decisopn Pending, Business Won, Rate not competitive, Business Discontinued, AR issues, Projects
[5 empty] | Need Assessment | Remove Meeting cancelled with remarks
[5 empty] | AR Followup | MOM-change to large text box
General

## Dispatch_relation
Pre-Dispatch_1
Dispatch number1 | Pre-Dispatch_1 | MAWB1 |  |  |  |  | Truck No
|  |  | HAWB1 | Invoice1 |  |  | Driver
[5 empty] | Stock1 |  | DL
[5 empty] | Stock2 |  | Truck Type
Stock3
|  |  | HAWB2 | Invoice2
Stock4
Stock5
Stock6
Dispatch number1 | Pre-Dispatch_1 | MAWB2
|  |  | HAWB3 | Invoice3
Stock7
Stock8
Stock9
|  |  | HAWB4 | Invoice4
Stock9
Stock10
Stock11

## Transport_Business_model
Customer | BusinessType | From Location | To Location | Min Distance (km) | Max Distance (km) | Vehicle Type | Rate (INR) | Remarks
A | Case To Case | L1 | L2 |  | NA | 20Ft | 100
A | Case To Case | L3 | L4 |  | NA | 20Ft | 200
B | Case To Case | L1 | L2 |  | NA | 20Ft | 150
B | Case To Case | L3 | L4 |  | NA | 20Ft | 250
A | Prime | NA | NA | 0 | 2250 | 20Ft | 51 | Rate per km | 100000 | 100000 | 100000
A | Prime | NA | NA | 2551 | 10000 | 20Ft | 21 | Rate per km | 2500 | 1800 | 2000
B | Prime | NA | NA | 0 | 2250 | ACE | 60 | Rate per km | 40 | 55.5556 | 50
B | Prime | NA | NA | 2551 | 10000 | ACE | 30 | Rate per km