## req_text
Sl No | Rdescription | Owner | Status | Remarks
1 | Capture Commodity details - Add in Gate-In Form (Change Stock Type to Commodity Type) (Garments, Auto Parts, Leather Garments, Shoe Uppers, Finish Leather, Console, Electrical & Electronics) - Jose (Venkat to send commodity details list) | Jose | Completed
2 | Return process to be detiailed | Venkat/Sridhar Sir | Hold | Need inputs from Sridhar Sir
3 | Rename Loading Bay to Goods Receipt | Jose | Completed
4 | Add E,D,S prefix to customer code | Jose | Hold | Need inputs from Sony/Venkat
5 | Add Not Available to OTL check in loading bay form | Jose | Completed
6 | Capture system timing for Unloading start & End Time | Jose | Hold | Recommend to implement this feature after go-live.
7 | Arrival Date & Time in Gate-In screen renamed as Dock-In Date & Time | Jose | Completed
8 | Remove Dock-In Date & time form loading bay form | Jose | Completed
9 | Check customer contract validity on customer selection in Gate-In form | Jose | YTS
10 | Notifications/alert for Customer Contract Validity, Warehouse Insurance Validity, Vendor contract Validity, E-way bill Validity | Jose | YTS
11 | In Gate-In Form, if customer contract validity is expired, further steps should be allowed only for super user | Jose | YTS
12 | In Gate-In form, change Invoice (actual) to Invoice weight-Gross(KG) | Jose | Completed
13 | Create Gate-In from Pre-Gate-In page | Jose | Hold | Since it has one to many releationship, technically its not advisable to create WH job from Pre-gatein form
14 | Module List access and permissions | Jose/Joseph Sir/Sridhar Sir
15 | Change E-way bill validity date field to date & time | Jose | Completed
16 | Check E-way bill validity (alert has to 4hr before validity) | Jose | YTS
17 | In Pre-Gate-In, add branch dropdown (for GRN purpose) | Jose | Completed
18 | In Pre-Check-In, add Shipment-Alert attachment (Shipment Information) | Jose | Completed
19 | In Pre-Check-In, Attachment for customer approval (in case of mismatch) | Jose | Completed
20 | In Billing, rate for all charges should be editable with concessional rate or Nil Billing with approval email from Customer/Joseph sire (Super user).Also, include comment box to document the change | Jose | YTS
21 | In Customer master creation, super user to approve deviation in mandatory document (KYC, Contract, SOW, Operations SOP, Billing SOP,Rate Sheet) requirement with comments. Each document attachment field should have deviation (Yes/No), Frequency (Time being/Permanent)(Time being alert should be notified in alerts, Comments | Jose | YTS
22 | In Damage Check/Before, change Damage Type to Multi select | Jose | YTS
23 | In Damage Check/Before, generate GRN branch wise continuous number (Chennai-MAA, Bengaluru-BLR-XXXXXX) | Jose | Completed
24 | Continuous Job Number unitwise (Ex: MAA-U1-XXXX) | Jose | Hold | Will be implemented during Go-Live
25 | Add GRN Number in Damage Check/After form | Jose
26 | Spell check Physical weight in Damage Check/After form | Jose
27 | In Damage Check/After Physical and Chargeable weight should be calculated for all box not for individual box | Jose
28 | In Damage Check/After form add comment box to document deviations | Jose
29 | In Damage Check/After change damage check button name to inspection check report | Jose
30 | In Damage Check/After inspection report should be downloadable for any condition | Jose
31 | In Damage Check/After rename Damages as Overage/Shortage and mention the count in next text box and move to Damage Check/Before form | Jose
32 | In Damage Check/After move Ratification process to Damage Check/Before form | Jose
33 | In Damage Check/After move rename Quantity deviation as Quantity deviation (in open Box) and move to Damage Check/Before form | Jose
34 | In Damage Check/After add Fumigation Status (Yes/No). If fumigation is No then add a drop down with options (BVM,Customer) Venkat/Raghu to provide further process when fumigation Â come under BVM | Jose
35 | Add "Marks & numbers" (yes/no) in "Damage Check/Before". If No, hold the process and proceed upon customer approval | Jose
36 | Rename "Damage Check/Before" to "Check/Before offloading" and "Damage Check/After" to "Inspection" | Jose
37 | In Warehouse-In form, branch and unit should be tagged to user id | Jose
38 | In Dispatch, add E-Waybill number, delivery challan | Jose
39 | In Dispatch, validate driver, truck, OTL with customer email | Jose
40 | In Loading Bay, move Dock-In time above Start time | Jose
41 | Share hardware configuration and cost for Tablet, QR Scanner, QR printer to BVM team | Jose
42 | Schedule recurring meeting for every Saturday | Jose