## Sheet1
Sl No | Software | Pending Points | Priority | Help Needed
1 | Sales | Reports in excle | High | BVM to provide the field and values to be displayed in Excel report
2 | Warehouse | email alert for DRS, stock in/Out to customer | High | 1. Lit of customer and emails for respective business 2. BVM email host details similar to shown below EMAIL_HOST = 'smtp.gmail.com' EMAIL_PORT = 587 EMAIL_USE_TLS = True EMAIL_HOST_USER = 'josevinoth83@gmail.com' EMAIL_HOST_PASSWORD = 'oygs mlgf bmxf tqoi'
3 |  | QR Scanning in production | low | Testing team required
4 |  | Multi-select option in invoice | medium | Testing team required
5 |  | reports | High | Please provide the expected filed names to be displayed in report.
6 | Packing | Goods retival | High | Details like project number, Po number, and customer name are to be considered for goods retrieval.
7 |  | Goods return to stock from production | High | Testing team required
8 |  | Generate delivery challan | medium | Gopi sir to provide the format
9 |  | Generate Gate Pass. When to generate gate pass and delivery challan | medium | Gopi sir to provide the format
10 |  | Add button to generate BOM (Wood, Plywood, Consumables) | medium | Testing team required
11 |  | In Costing Summary add form, Clone quotation summary | medium | Testing team required
12 |  | The nearest stock size should come on top and add an alert message to inform the user about the oldest stock. | medium | Testing team required
13 |  | Add 'Special Requirements' as a drop-down field Multi-select with NA. | medium | Mansoor to provide the current list of requirements and Sony to append the requirements.
14 |  | Excess quantity compared with request and issue should be reported as below. (Separate forms) a. Consumption b. Stores return - PO and customer name c. | medium | Scrap - template to be provided by Sony
15 |  | Scrap approval process | medium | Joseph Sir