## req_text
Sl No | Backlogs | Module | Owner | Assinged on | Bug/Improvement? | Implemented On | Implemented By | Status | Remarks
1 | Capture Commodity details - Add in Gate-In Form (Change Stock Type to Commodity Type) (Garments, Auto Parts, Leather Garments, Shoe Uppers, Finish Leather, Console, Electrical & Electronics) - Jose (Venkat to send commodity details list) | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
2 | Return process to be detiailed | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | Need inputs from Sridhar Sir
3 | Rename Loading Bay to Goods Receipt | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
4 | Add E,D,S prefix to customer code | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | Need inputs from Sony/Venkat. Decided to provide manual input
5 | Add Not Available to OTL check in loading bay form | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
6 | Capture system timing for Unloading start & End Time | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | Recommend to implement this feature after go-live.
7 | Arrival Date & Time in Gate-In screen renamed as Dock-In Date & Time | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
8 | Remove Dock-In Date & time form loading bay form | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
9 | Check customer contract validity on customer selection in Gate-In form | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
10 | Notifications/alert for Customer Contract Validity, Warehouse Insurance Validity, Vendor contract Validity, E-way bill Validity | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
11 | In Gate-In Form, if customer contract validity is expired, further steps should be allowed only for super user | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
12 | In Gate-In form, change Invoice (actual) to Invoice weight-Gross(KG) | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
13 | Create Gate-In from Pre-Gate-In page | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | Since it has one to many releationship, technically its not advisable to create WH job from Pre-gatein form
14 | Module List access and permissions | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
15 | Change E-way bill validity date field to date & time | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
16 | Check E-way bill validity (alert has to 4hr before validity) | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
17 | In Pre-Gate-In, add branch dropdown (for GRN purpose) | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
18 | In Pre-Check-In, add Shipment-Alert attachment (Shipment Information) | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
19 | In Pre-Check-In, Attachment for customer approval (in case of mismatch) | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
20 | In Billing, rate for all charges should be editable with concessional rate or Nil Billing with approval email from Customer/Joseph sire (Super user).Also, include comment box to document the change | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
21 | In Customer master creation, super user to approve deviation in mandatory document (KYC, Contract, SOW, Operations SOP, Billing SOP,Rate Sheet) requirement with comments. Each document attachment field should have deviation (Yes/No), Frequency (Time being/Permanent)(Time being alert should be notified in alerts, Comments | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
22 | In Damage Check/Before, change Damage Type to Multi select | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
23 | In Damage Check/Before, generate GRN branch wise continuous number (Chennai-MAA, Bengaluru-BLR-XXXXXX) | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
24 | Continuous Job Number unitwise (Ex: MAA-U1-XXXX) | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | Will be implemented during Go-Live
25 | Add GRN Number in Damage Check/After form | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
26 | Spell check Physical weight in Damage Check/After form | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
27 | In Damage Check/After Physical and Chargeable weight should be calculated for all box not for individual box | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | At present Physical and Chargeable weight calculated for group of packages which is required to measure weight & Dimension deviation
28 | In Damage Check/After form add comment box to document deviations | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
29 | In Damage Check/After change damage check button name to inspection check report | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
30 | In Damage Check/After inspection report should be downloadable for any condition | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
31 | In Damage Check/After rename Damages as Overage/Shortage and mention the count in next text box and move to Damage Check/Before form | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed | Change in no of units deviation to be mentioned in comment box. For consistency, Overage/Shortages retained as "Quantity Change"
32 | In Damage Check/After move Ratification process to Damage Check/Before form | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
33 | In Damage Check/After move rename Quantity deviation as Quantity deviation (in open Box) and move to Damage Check/Before form | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
34 | In Damage Check/After add Fumigation Status (Yes/No). If fumigation is No then add a drop down with options (BVM,Customer) Venkat/Raghu to provide further process when fumigation Â come under BVM | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
35 | Add "Marks & numbers" (yes/no) in "Damage Check/Before". If No, hold the process and proceed upon customer approval | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
36 | Rename "Damage Check/Before" to "Check/Before offloading" and "Damage Check/After" to "Inspection" | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
37 | In Warehouse-In form, branch and unit should be tagged to user id | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed
38 | In Dispatch, add E-Waybill number, delivery challan | WMS | BVM Team | 2022-09-24 |  | 2023-01-01 | Jose | Completed | Like to know what content to be added in delivery Chellan
39 | In Dispatch, validate driver, truck, OTL with customer email | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | Validation controlled by process
40 | In Loading Bay, move Dock-In time above Start time | WMS | BVM Team | 2022-09-24 |  |  |  | Hold | As per point 8, Dock-In time removed from loading bay form
41 | Share hardware configuration and cost for Tablet, QR Scanner, QR printer to BVM team | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
42 | Schedule recurring meeting for every Saturday | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
43 | in add/update insurance, include insured amount and premium | WMS | BVM Team | 2022-09-24 |  |  |  | YTS
44 | In customer data, add email field for operations lead | WMS | Sony | 2022-12-22 |  |  |  | YTS
45 | Remove Checked-In Status in Warehouse-In form | WMS | Jose | 2023-01-07 |  |  |  | YTS
46 | To be aligned as per the Process and not and alphabetic order | WMS | Jose | 2023-01-09 |  |  |  | YTS
47 | Commodity list to be provided for Masters | WMS | Venkat | 2023-01-09 |  |  |  | YTS
48 | Pre-Gatein (OTL, Lock & Key, NIL) | WMS | Jose | 2023-01-09 |  |  |  | YTS
49 | To work on Shipper invoice currency | WMS | Sridar Sir | 2023-01-09 |  |  |  | Cancelled | Currency value should match invoice. So existing process holds good.
50 | In Damage Check/Before Offloading change Quantity Deviation to Packages Deviation | WMS | Sridar Sir | 2023-01-09 |  |  |  | Completed | Retaining "Quantity Deviation" instead of "Package Deviation"
51 | In Damage Check/Before Offloading when Damages is not 'Nill Damage' or Quantity Devition or Ratification Process or Marks & Numbers is 'No' then Status should be 'Hold' | WMS | Sridar Sir | 2023-01-09 |  |  |  | Completed | Retaining "Work In Progress" instead of hold.
52 | Include camera option to upload the pics. | WMS | Sridar Sir | 2023-01-09 |  |  |  | YTS
53 | Fumigation Status - Inspection screen | WMS | Sridar Sir | 2023-01-09 |  |  |  | Completed
54 | Check Fumigation | WMS | Sridar Sir | 2023-01-09 |  |  |  | Completed
55 | In the inspection tab capture the weight and no of pacakages deviation | WMS | Sridar Sir | 2023-01-09 |  |  |  | YTS
56 | In Warehouse in tab check no of pieces is considered for storage. | WMS | Jose | 2023-01-09 |  | 2023-01-11 | Jose | Completed
57 | View option to be creasted for sridhar sir | WMS | Sridar Sir | 2023-01-09 |  |  |  | YTS
58 | DSR | WMS | Venkat | 2023-01-09 |  |  |  | YTS
59 | In storage report tab check the date formating for the check-out time | WMS | Sridar Sir | 2023-01-09 | Bug | 2023-01-14 | Jose | Completed
60 | Packing Type : Wooden Case, Carton Box, Ply wood. If wooden case : Fumigation to appear. Fumigation : Yes & No. Yes to be completed. No : Customer or BVM (colour code). BVM : Date to be filled and accordingly. If fumigation done by BVM then, the cost should be included in billing. | WMS | Prakash | 2023-01-11 | Improvement | 2023-01-14 | Jose | Completed | Billing for fumigation alone pending
61 | Dimension : Multiple line items to be clubbed | WMS | Prakash | 2023-01-11 |  |  |  | YTS
62 | Empty truck photo to be in warehouse in tab | WMS | Prakash | 2023-01-11 |  |  |  | Cancelled | Already available in "Damage Check Before/Offloading" orm
63 | Multiple MAWB & HAWB to be added | WMS | Prakash | 2023-01-11 |  |  |  | YTS
64 | In warehousemaster rate form, bring customer short name in drop down | WMS | Sony | 2023-01-12 |  |  |  | YTS
65 | In Goods report form, headers are not alinged in with content. Check in similar forms as well. | WMS | Sony | 2023-01-12 |  |  |  | WIP
66 | Re-Order side Nave in WMS. Pre-Gate In, Warehouse Jobs, Goods Report, Dispatch, Invoice, Reports, WMS Misc. | WMS | Sony | 2023-01-12 |  | 2023-01-12 | Jose | Completed
67 | In Stock Value report, round off total to 2 decimal places. | WMS | Jose | 2023-01-12 | Improvement | 2023-01-12 | Jose | Completed
68 | In Gate-In Form, don’t show pre-gatein ID's for checked out jobs | WMS | Jose | 2023-01-13 | Improvement |  |  | Cancelled | Since pre-gatein number linked to multiple WH jobs, its not possible to remove from list.
69 | WMS dashboard: Pending for invoice and bring reports to WH dashboard | WMS | Sony | 2023-01-14 | Improvement |  |  | YTS
70 | In invoice, partial billing to be calculated. | WMS | Sony | 2023-01-14 | Improvement |  |  | YTS
71 | In WMS dashboard, show goods older than 7 days | WMS | Sony | 2023-01-14 | Improvement |  |  | YTS
72 | Add total invoice weight in inspection sheet. Entering weight for each box is not feasible. | WMS | Venkat | 2023-01-18 | Improvement |  |  | Hold | To be discussed with Sridhar Sir
73 | Check INR Calculation | WMS | Venkat | 2023-01-18 | Bug | 2023-01-19 | Jose | Completed
74 | Add PO number | WMS | Venkat | 2023-01-18 | Improvement | 2023-01-25 | Jose | Completed
75 | Check chargable weight and CBM calcualtion | WMS | Venkat | 2023-01-18 | Bug | 2023-01-18 | Jose | Completed
76 | Prepare sock reprot as per DSR shared by venkat | WMS | Venkat | 2023-01-18 | Improvement |  |  | YTS
77 | In inspection form, Add goods count & weight comparison between invoice and check-In | WMS | Jose | 2023-01-25 | Improvement | 2023-01-25 | Jose | Completed
78 | In Inspection form, check-In weight and count throwing round off error | WMS | Prakash | 2023-01-27 | Bug | 2023-01-27 | Jose | Completed
79 | In inspection form, remove validation for excess weight | WMS | Prakash | 2023-01-30 | Improvement | 2023-01-31 | Jose | Completed
80 | Once Dispatch status is completed, update Dispatch status t "Yes" in gatein table database | WMS | Prakash | 2023-01-30 | Improvement | 2023-01-31 | Jose | Completed
81 | Audit Module for TMS WMS PMS - Audit Manual, checklist, score card and reports | WMS | Sridhar | 2023-02-03 | Improvement |  |  | YTS | Sridhar sir to provide detailed requirement.
82 | Sales Management System (SMS) | WMS | Sridhar | 2023-02-03 | Improvement |  |  | YTS | Sridhar sir to provide detailed requirement.
83 | Insurance Module to be changed | WMS | Sridhar | 2023-02-03 | Improvement | 2023-02-11 | Jose | Completed | Sony to provide more details.
84 | Budget Master to be created. Branch,Unit, Expnse type, amount, month | WMS | Sridhar | 2023-02-03 | Improvement |  |  | YTS | Sony to provide more details.
85 | In expense add form, service start and end date to be same | WMS | Sridhar | 2023-02-03 | Improvement |  |  | YTS | Sony to provide more details.
86 | Income Master line item to be defined | WMS | Sridhar | 2023-02-03 | Improvement |  |  | YTS | Sony to provide more details.
87 | Check remarks field for Inward, storage and dispatch | WMS | Sridhar | 2023-02-03 | Improvement |  |  | YTS
88 | In Dispatch form, increase text field size | WMS | Prakash | 2023-02-16 | Improvement | 2023-02-16 | Jose | Completed
89 | Create route master | TMS | Sony | 2023-02-18 | Improvement |  |  | YTS
90 | In Trip details, move 'Delivery Image' and 'Proof Of Delivery' to Trip closure. | TMS | Sony | 2023-02-18 | Improvement |  |  | YTS
91 | In Vehicle master, vehicle details, enginer number should be alpha numberic | TMS | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
92 | In Vehicle master, vehicle details battery number should be alpha numberic | TMS | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
93 | In Vehicle master, insurance details insurance copy should be attachable | TMS | Karthik | 2023-02-18 | Improvement |  |  | YTS
94 | In Vehicle master, RTO details FC copy should be attachable | TMS | Karthik | 2023-02-18 | Improvement |  |  | YTS
95 | In Vehicle master, RTO details Road Tax copy should be attachable | TMS | Karthik | 2023-02-18 | Improvement |  |  | YTS
96 | In Vehicle master, Permit and pollution control details permit copy should be attachable | TMS | Karthik | 2023-02-18 | Improvement |  |  | YTS
97 | In Vehicle master, Permit and pollution control details pollution certificate copy should be attachable | TMS | Karthik | 2023-02-18 | Improvement |  |  | YTS
98 | In vendor add form, GSTIN number set size to 15 | TMS | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
99 | In Expense add form, split total bills into multiple line items. | TMS | Blessy | 2023-02-18 | Improvement |  |  | YTS
100 | In Vehicle master, change ICV to IDV | TMS | Karthik | 2023-02-18 | Improvement | 2023-02-18 | Jose | Completed
101 | In Consignment note add, add customer code | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
102 | In Enquiry note add, aassigned to should be from login user | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
103 | In Consignment note add, add touch point between from and to | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
104 | In Consignment add, consigner, consignee,Consigner Invoice, Consigner Value, Value in INR, No of Pieces, weight to be added as separate line item | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
105 | In Consignment add, move ebill no, date of Issue, Date of validity to trip details form | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
106 | In Consignment add,remove 'Container' for 'Container Description' label. | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
107 | In Consignment add,remove Dimension | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
108 | In Consignment add,add 'Movement type' with FTL, LTL as drop down | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
109 | In Consignment add,change 'Movement' to 'Consignent Type' | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
110 | In Consignment add,change 'Movement' to 'Consignent Type' | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
111 | In Consignment add,add 'Freight Amount' | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
112 | In Tripdetails add, include 'Biling Type' drop down. Vehicle Type Requested, Vehicle Type Placed | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
113 | In Tripdetails add, change 'Vehicle Type' label to 'Vehicle Type Placed'. | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
114 | In Tripdetails add, update driver name as drop down and pull license number, contact number from database | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
115 | In Tripdetails add,From Location, To Location, Starting Km, Ending KM, Starting Date, Ending Date as seprate Row Items | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
116 | In Trip closure, change 'cost' in all labels to 'Charges' | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
117 | In Trip closure, add 'Handling Charges and Halting Charges | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS
118 | In Trip closure, add customer ref no | TMS | Sony | 2023-02-21 | Improvement |  |  | YTS

## Expense
BRANCH | UNIT | VENDOR | VENDOR BILL NO | VENDOR BILL DATE | Service Start Date | Service End Date | EXPENSE Type | UNIT OF MEASUREMENT | RATE | REMARKS | QUANTITY | AMOUNT | GST RATE % | GST AMOUNT | TOTAL AMOUNT | TDS RATE % | TDS AMOUNT | AMOUNT PAYABLE | DUE DATE | PAID DATE
FK | FK | FK | text | Date |  |  | Man power | FK | Float | textarea | int | float | float | float | float | float | float | float | date | date
[7 empty] | rent | Sqt |  |  |  |  | 18% |  |  |  | amount*tds rate | tot amount-tds amount | bill date +vendor payment (check vendor database)
[7 empty] | security | Nos
hrs

## Project_Progress
WMS | TMS | PMS | Sales | Admin | AR | Assets | Employee
90% | 60% | 0% | 0% | 70% | 0% | 70% | 80%